## Sheet1
Risk Register
Prepared by: |  | R&D group |  |  | Date: | 2020-07-28
| Versions | Date
| 1 | 7/8/2020 - 1/10/2020
| 2 | 1/10/2020 - 31/10/2020
| 3 | 31/10/2020 -
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 |  | Project proposal delay | Missing the due date for project proposal | Schedule |  | Submit after due date | Monitor project proposal status regularly | Zureen Hanif | Low | High | Closed
2 |  | Birth | Leen giving birth close to presentation date | Human |  | giving birth before date of presentation | -Follow up with project leader on this matter. Pre record presentation | Leen Alzebn | High | Medium | Closed
3 |  | Global Pandemic | COVID 19 returns causing educational facitilies to shut down | Environmental | COVID 19 | Increased cases in COVID 19 | Continue communcations and collaborations through online resouces. Follow up with project sponser | Jayden Kean | High | Medium | Open
4 |  | Project Purpose | Project purpose is not well defined | Quality |  | Project purpose is weak | Complete business case and cleary define the purpose | Miracle Pule | Low | High | Closed
5 |  | Lack of Communication | Lack of communication causing lack of clarity and confusion | Communication |  | Team is not communicating regularly and effectively | -Complete communication plan with team. Have face to face meetings | Harpreet Singh | Medium | High | Closed
6 |  | Slow feedback | Getting slow feedback from mentor/project sponser and client causing delay in project progress | Communication |  | Client/Mentor responses are slow | - Request an urgent contact method from client/mentor | Miracle Pule | Medium | High | Closed
7 |  | UWB tag | System is not recognising UWB tag location | Technical/Coding | Error in coding | UWB tag is not responding | -Monitor configuration settings for UWB tag. Check for any compiler errors | Miracle Pule | Medium | Medium | Open
8 |  | Skills Analysis | Team does not cover all the skills required for the project | Human |  | Skillset missing in the project | Complete skills register and identify any gap missing. Upskill on areas that are required for the project | Miracle Pule | Low | High | Closed
9 |  | Imported Resources | Due to travel restrictions, import of resources for the project might be delayed | Schedule | COVID 19 |  | -Request resouces from inside NZ | Miracle Pule | Low | Medium | Closed
10 |  | Translation mannual | Cannot make sense of translation of documents from client | Communication |  | Translating text online | Follow up with client on accurate translation | Leen Alzebn | Medium | Medium | Closed
11 |  | Lack of motivation | Team members are feeling unmovitated being unable to have face to face communications with team, client and mentors | Communication | COVID 19 | Tasks are not being completed. Poor communication with team | Project manager to check in with each team member reguarly | Zureen Hanif | Low | Medium | Open
12 |  | UWB tag positioning error | UWB tag positioning is inaccurate due to module signal being blocked by obstacles | Technical/Coding |  | Having obstacles too close to the module | Keep module at least 1m away from obstacles | Miracle Pule | Low | Medium | Open
16 |  | Team members affected from COVID | Team members having symptoms of corona virus which will affect their participation in project | Medical | COVID 19 | Having symptoms of coronoa virus | Self isolate to prevent the spread of the disease | Miracle Pule | Low | High | Open
17 |  | Damage to hardware | Physically damaging the hardware or losing the hardware by misplacing it | Technical |  | Physically damaged from mishandling | Read documents sent by client on the hardware | Miracle Pule | Medium | High | Open
18 |  | Document signature | The documents requested by client not able to be signed off by AUT | Communication |  | Not having permission from AUT to sign documents requested by client to continue the project | Follow up with project sponser | Miracle Pule | Medium | High | Open
19 |  | Auckland moves back to level 3/4 Lockdown due to COVID 19 | Team will be unable to interact physically to work on the project which will cause a delay in progess | Communication | COVID 19 | Increase number of cases | -Move to online meetings | Miracle Pule | Medium | Medium | Open